## Impact
The Monitoring Matrix - IMPACT LEVEL
Result | Indicator/Progress Marker | Baseline Value (2015) | Final Target Value (2020) | Target Value Yr 1(2016) | Actual Value 2016 | Comments on 2016 Value | Target Value Yr 2 (2017) | Target Value Yr 3 (2018) | Target Value Yr 4 (2019) | Target value Yr 5 (2020) | Unit of Measurement | Source of Verification | Frequency Data collection | Start - End Measurement | Responsible data collection | Responsible Consolidation | Other[1]
IMPACT: Employability of youth is improved through better quality of instruction and learning in skills development: | Number and % of trained graduates in project area absorbed in labour market or self employed (male / female) 6 months after graduation | N/A | 50% | N/A | 0% | Training yet to start | 15% | 20% | 10% | 5% | Number and Percentage | Tracer studies in project area | Annual | Start - 0 End - 50% | Project | Project | Tracer studies
| % of employers satisfied with BTVET graduates (male / female) | N/A | 66% | N/A | 0% | Employer survey to be conducted in 2017 | 10% | 20% | 30% | 6% | Percentage | Employer satisfaction survey | Annual | Start - 0 End - 66% | VTI, Field Coordinators | M&E | Employer survey
| % of graduates (Gender, Vulnerable youths, refugees, region) that indicate that their socioeconomic situation (income/livelihood) has improved, 6 months after graduation? | Baseline value needed | 50% | 0 | 0 | On schedule | 10% | 15% | 20% | 5% | Percentage | Tracer studies | Annual | Start ; End 50% | RTF / Project | MoES M&E dep.
| Role of the private sector (PPP) in BTVET planning, decision making and implementation (qualitative description) at the sector level, regional and national level. | N/A | Systemic involvement of PS in SDA | Adhoc | Adhoc | On schedule | Active participation of SSCs and SDCs in SD | SSCs and SDCs playing a central role in SD | Systemic through SDA | Policy guidelines for PPPs etablished | Qualitative measure | SSCs Reports, SDCs Reports, Project PPs | Annual | Start: Little Involvement End: Greater Involvement | RTF / Project | SDA | Adhoc, Levels ie USSIA, VTI, RTF (50%) Governing Councils
| Levels of implementation of the paradigm shift in SD (5 Skilling Uganda strategy indicators) | 0/5 | 5 out of 5 SU Indicators | 0 | 0 | On schedule | 2 out of 5 | 3 out of 5 | 4 out of 5 | 5 out of 5 | Number | SDA Reports, RTF | Annual | Start 0; End 5 | SDA, MoES | SDA | Check RTF MTR
| Perceptions regarding BTVET in society | Negative Image | Positive Image | Moderate image | Negative image | Tracking system to be put in place | Moderate image | Moderate with good practices | Fairly positive image | Fairly positive image | Qualitative measure | Radio tracking (UN system), Opinion polls | Annual | Start: Negative image End: Positive image | Communications Unit | Communications Unit
| Diversified & Sustainable funding to skills development (sources: PPP financing of BTVET) (NPA) | N/A | Increased financing of skills development | Joint ventures of training providers and private sector | None signed | Work in progress | Sustained joint ventures | Increased financial commitmnet by the private sector | Policy guidelines for PPPs | Policy guidelines for PPPs etablished | Qualitative measure | National reports, NSDF | Annual | 2016-2020 | NPA | NPA | Check NPA Indicators
| Local Economic Growth in priority sectors in project areas | Baseline | Improved standards of living | Increased level of IGAs | Not measured | Not Measured | Diversified economic activities | Increased productivity | Increased income | Increased income and livelihoods | Qualitative measure | Income reports | Annual | 2016-2020 | UBOS | UBOS
| Number of partner institutions that qualify as centre of excellence (level of achievement (criteria ?) | N/A | 5 Institutions | 0 | 0 | On schedule | 0 | 0 | 3 | 2 | Number | CoE accreditation doc | End evaluation | Start: 0 End: 5 | SDA (Project) | Project

## Outcome Level
The Monitoring Matrix - OUTCOME LEVEL
Result | Indicator/Progress Marker | Baseline Value (2015) | Final Target Value (2020) | Target Value Yr 1 (2016) | Actual Value 2016 | Comments on 2016 value | Target Value Yr 2 (2017) | Target Value Yr 3 (2018) | Target Value Yr 4 (2019) | Target Value Yr 5 (2020) | Unit of Measurement | Source of Verification | Frequency Data collection | Start - End Measurement | Responsible data collect | Responsible Consolidation | Other[1]
OUTCOME: The quality of skills development is enhanced and responsive to labour market needs in line with the skilling Uganda reforms. | RESULT 1: System Change/Paradigm Shift: Governance structure ensures responsiveness of skills development activities to labor market needs
| SDA formally established and operational | N/A | SDA | 0 | 0 | Etablishment of SDA was not foreseen in 2016 | 0 | Process to establish SD agency near completion |  | SDA | Qualitative | NPA Report, SDA Report | Annual | Start 0 - End 1 | NPA, RTF | RTF | NPA Indicator
| Number of SSCs and SDCs established and contributing to making SD relevant | 5 SSCs, 0 SDCs | 14 (9 SSCS, 5 SDCs) | 5 SSCs | 5 SScs | Value remained as 5 SSCs | 5 SSCs | 9 SSCS, 5 SDCs | 9 SSCS, 5 SDCs | 14 | No of SSCs/ SDCs | RTF reports, SDA Reports, NPA Monitoring reports | Quarterly | Start 5, End 14 | RTF,SDA | RTF/Quality Assurance Directorate
RESULT 2: Piloting SDF: SDF grant recipients provide quality skills development programs that are responsive to labor market needs
| Level of adoption/ handing over of SDF management system to national authorities | N/A | SDF handover to national authorities | 0 | 0 | SDF still at inception phase and being test run | Document and best practices | Sharing documented experiences | Refine SDF and handover | SDF handed over to national authorities | Qualitative | SDF System | Annual | Start - 0: End - 1 | RTF/SDA | SSU Project | Dependent on SDA Establishment
| Number and % of SDF grant recipients that continue with improved practices (e.g. partnerships / WBL) 6 months after project | N/A | 60% | 10% | 0% | SDF grant recepients yet to be identified and Grant Agreements yet to be signed | 15% | 20% | 20% | 5% | Percentage | Tracer studies, followup reports of partners | Annual | Start 0: End 60% | RTF/SDA | RTF/SDA
| The level of integration of green skills, gender mainstreaming, life skills, HIV, entrepreneurship skills in the new short term training modules. | N/A | 50% of grantees integrate cross cutting themes | 10% | 0% | Development of short term training modules to start in 2017 | 15% | 30% | 40% | 50% | Reports/ Assesement criteria | SDA Reports, DIT Reports | Bi - Annual | Start 0: End 50% | SDF Unit | M&E
| Number of SDF beneficiaries that have enhanced their skills through instant (10-100 hours) courses responding to identified skills gaps for green economy, livelihood & market development and service delivery (disaggregated by vulnerability / gender origin / refugee) | N/A (Studies of WN & Karamoja) | 2500 of whom 30% women (500-Albertine, 1,000 EUTF, 1,000 Karamoja) | 0 | 0 | on schedule | 700 | 1000 | 500 | 300 | Number | Tracer studies | Annual | Start- 0: End -2,500 | Implementing partners | M&E | Potential collaboration
| Number of SDF beneficiaries (disaggregated: vulnerability / gender / origin / refugee) that participate in training in formal BTVET and entrepreneurships training in order to enhance employable skills. | N/A | 3500 of whom 30% women (Albertine 1500, Karamoja 1000, EU 1000) | 450 | 0 | Training to start in 2017 | 1000 | 1000 | 1000 | 500 | Number | Reports, database, Tracer studies | Annual | Start- 0: End -3,500 | Implementing partners | M &E, SDF Unit | Potential collaboration
| Utilization rate of start-up kits after 6 months after disbursement | 0 | 40% utilisation | 0 | 0 | on schedule | 10% | 15% | 10% | 5% | Percentage | Tracer studies, followup reports | bi-annual | Start 0: End 40% | Implementing partners | M&E | Beneficiaries encouraged to build safe guard measures for their startup kits
RESULT 3: Support to Establish Centers of Excellence: Centers of Excellence provide quality skills development programs, that are responsive to labor market needs
| No. and % of beneficiaries (men/women) that have received a certificate in accordance with employer needs, through a recognized technical and vocational certification body (e.g. Workers’ Pas / City and Guilds, etc.) and in employment or self employed. | Baseline data needs collection from SSU 7 VTIs | 70% completed course and certified compared to enrolled | 20% completed and certified | 0% | Target of 20% was a some what ambitious. Baseline for the 5 partner VTIs to be conducted in the Albertine and Rwenzori region. | 30% completed and certified | 40% completed and certified | 50% completed and certified | 70% completed and certified compared to enrolled | Percentage | Certification records | Annually | Start: ?; End: 70% | VTIs | Project
| Percentage Increase in number of trainees enrolled in priority sectors in the 7 VTIs | Baseline information from VTI Business Plans | 30% increase in enrolment in the priority sectors | 10% increase | 0% | Target not achieved. To collect baseline data for 2015/2016 | 15% increase | 20% increase | 25% increase | 30% | Number | Enrolment records from VTIs | Annually | Start: ?; End: 30% | VTIs&FCs | M&E
| Score on self-assessment tool for partner institutions scoring on: (Relevance / Quality / Equitable Access / Effective Management / Efficiency and resource mobilization | 1.3 out 4.0 | Average Self Assessment scores incease to 2.6 out of 4.0 | 1.3 out of 4.0 | 1.3 | Baseline value was maintained | 2.0 out of 4.0 | 2.4 out of 4.0 | 2.5 out of 4.0 | 2.6 out of 4.0 | Scores | Follow up Self assessemt reports for the partner VTIs (spider diagrams) | Annual | Start 1.3: End 2.6 out of 4.0 | Field staff & VTI | M&E | Self assessment Workshops may be done after project implementation
| Percentage and number of hours trainees spend engaged in WBL vis a vis number of hours trainees spend in BTVET Institution | Needs collection from VTIs | 25% | 5% | To be filled | Collection of industrial training assessment forms from the partner VTIs is underway in order to compute the %ages. | 10% | 15% | 20% | 25% | Percentage | Training records from private companies, Training focal person | Annual | Start ?: End 25% | Field staff & VTI | M&E

## Output Level
The Monitoring Matrix - OUTPUT LEVEL
Result/Indicator/Progress Marker | Baseline Value (2015) | Final Target Value (2020) | Target Value Yr 1 (2016) | Actual Value 2016 | Comments on 2016 Value | Target Value Yr 2 (2017) | Target Value Yr 3 (2018) | Target Value Yr 4 (2019) | Target Value Yr 5 (2020) | Unit of Measurement | Source of Verification | Frequency Data collection | Start - End Measurement | Responsible data collect | Responsible Consolidation | Other[1]
OUTPUT 1: System Change: Capacity of stakeholders is improved in relation to the skilling Uganda strategy
No. of priority sector labour market scans (LMS) (including TNAs) and livelihood studies conducted in the project areas and utilized by partner institutions for skills development training. | World Bank (Oil & Gas); RTF Western Region | 6 Comprehensive LMS studies | 0 | 0 | No study was planned for 2016 | West Nile 1; Karamoja 1 | Albertine 1 | West Nile 1; Karamoja 1 | 1 | No. of LMS, No. of livelihood studies | Field Monitoring Reports, Training Curiculum Monop, MoRE report, LMS, livelihood studies, SDF report, training curriculum | Annually | Start - 2 End - 11 | SSU PMT | M&E, Field Team | Potential collaboration with other actors
Level of integration of cross-cutting issues (gender / HIV / environment ) in the conducted studies above (scoring on a number of criteria tbd). | N/A | 80% consideration of Cross cutting issues in 9 studies | 50% in | 0% | Criteria of intergrating CCI in the studies underway | 50% intergration in 9 studies | 80% intergration in 9 studies | 80% intergtration in 9 studies | 80% Intergration in 9 studies | % level of intergration of CCI | LMS, Livelihood studies, ToRs for the studies | Annually | Start - 0 end - 80% | SSU PMT | Gender & Vulnerable Youth Officer | To base on agreed CCI criteria
No. of Training initiatives undertaken (training / study tours / bench marking / exchange visits) conducted for SDA, SDC, SSC) | 3 | 11 (5 for SDA, 3 for SSC & 3 for SDCs) | 3 ie Italy, India | 3 | 3 done, on target | 3 | 4 | 4 | 11 | No. of capacity building initiatives | SDA, DIT, Training reports | Annually | Start -5 End - 11 | SSU PMT | M&E | Italy, Kigali, Mauritius,Belgium, India
No. of people possessing and practising modern BTVET skills as a result of training. | N/A | 250 | 0 | 0 | Skills Training to start in 2017 | 50 | 50 | 50 | 100 | SDA proposal | SDA, RTF |  | Start - 0 End 250 | SSU PMT | M&E | Stakeholders trained in modern BTVET practices and practicing.
OUTPUT 2: Piloting SDF: Skill Development Fund system operational in the project area, serving as a model for the future national skills development fund.
No. of short term training modules developed/upgraded and formalized, based on local livelihood and labour market needs. | 0 | Atleast 20 trainings/niches for which new or adapted programmes are developed. | 5 | 0 | Development of training modules re-scheduled to 2017 | 5 | 5 | 5 | 5 | Number | Training modules, DACUM Reports | Annual | Start - 0: End - 20 | Implementing partners | M &E, SDF Unit | Potential collaboration with other actors
SDF grant system set-up and operational including: manual of operations, fund guidelines for specific baskets. | N/A | SDF system hand over | Grant system set up | Grant System partially set up | Partially achieved, work in progress | Grant system set up | Grant system operational | Grant system operational | System handover at national level | System | Grant system, Manual of operations, Reports | Annual | Start - 0: End - System Handover | SDF Unit | M&E | System setup wil be a gradual process
Volume of grant agreements signed through SDF | N/A | 4.6 million Euros | 0 | 0 | On schedule | 1.500.000 million Euros | 2.530.000 million Euros | 590.000 million Euros | 4.6 million Euros | Euros | Volume of money spent, number of Grant agreements signed | Annual | Start - 0: End - 4.6 m | SDF Unit | M&E | To be analysed per window
Number of awareness + promotions campaigns conducted for enhancing the participation of vulnerable groups (youth, girls, Karamojongs,refugees) | N/A | 45 | 3 | 15 | Exceeded target | 17 | 15 | 5 | 5 | Number | Tracking list of SDF info sessions, Reports | Quarterly | Start - 0: End 45 | SDF Unit | M&E | Radio talk shows, Print media and Stakeholder forums
OUTPUT 3: Support to Establishment of Centres of Excellence : Accessible BTVET centers of excellence, with special attention to BTVET needs and potentials of women and girls.
No. of formal agreements signed with the private sector (PPPs) | N/A | 14 | 3 | 0 | No agrements signed yet however, the process for collaboration with the private sector (UMA,USSIA, etc) already started. | 5 | 4 | 3 | 2 | Number | Copies of agreements signed | Annually | Start: 0 End: 14 | SSU | M&E | 2 agreements per institution
Number of instructors trained in priority sectors in relation to WBL programs, and using the skills | VTI self assessments | 70 | 10 | 0 | Program for training instructors is being developed | 20 | 20 | 20 | 10 | Number | Training reports, List of instructors trained Training programs (Lesson plans) | Annually | Start: ? End: 70 | Field staff | M&E
Number of Private Sector mastercrafts persons trained in priority sectors and in relation to WBL programs | 126 trained in all sectors at mastercraft level | 500 master craft persons trained in priority sectors vis avis other sectors | 50 | 0 | Mobilisation and sensitisation in Albertine region done, Training to start in February 2017. Mobilisation for Karamoja region to be initiated. | 150 | 150 | 150 | 50 | Number | Training reports, List of trained mastercrafts | Annually | Start - 126; End 500 | Field staff | M&E
No. of CBT curricula developed/upgraded and intergrated with crosscuting issues and training programs conducted based on labour market needs (NPA/SU) | N/A | Long term courses: 12 Short Term courses: 20 | Long term courses: 2 Short Term courses: 4 | 0 curricular developed | Assessment of CBT curriculum is underway then deveopment of DACUM profiles using DACUM approach for the 6 priority trades | Long term courses: 4 Short Term courses: 5 | Long term courses: 3 Short Term courses: 5 | Long term courses: 3 Short Term courses: 5 | Long term courses: 2 Short Term courses: 5 | No. of curricula | NCDC, DIT Reports, VTI Reports | Annually | Start: 0 End: Long term courses: 12 Short Term courses: 20 | NPA, (Project) | Project | Check with NPA, Liase with NCDC
No. of BTVET institutions and facilities rehabilitated, expanded and equipped (NPA) | N/A | 7 Institutions | 0 | 0 | On course. Preparations underway | 0 | 60% completed | 80% completed | 100% completed | No. of institutions rehabilitated, expanded and equiped | Progress reports, Grant Agreements, NPA | Monthly during construction phase | Start-0: End-7 | PMT | PMT & MoES | Specific details of the work will only be determined after each institution has prioritised and budget alocated
% increase and Number of enrolled target beneficiaries (disaggregated: vulnerability/gender/origin/ refugee) that attain CBET qualifications | To be collected from the VTIs database | 30% increase of Vulnerable Youth and 30% increase of females | 5% | 0% | Collection of baseline data on current enrollment (disaggregated) is underway | 10% | 15% | 20% | 30% | % increase, number | Enrollement data | Annually | Start: End 30% | Field team, VTIs | M&E | Establish numbers from project field team
Number and % of beneficiaries (men/women) that participate in training in non-formal & formal BTVET (with entrepreneurship component) in order to enhance employable skills | N/A | At least 30% girls and women and (70% Karamojong in Karamoja program) 800 West; 200 Karamoja | 5% women; 10% Karimojong | 0% | Training to start in 2017 | 10% women; 30% Karimojong | 15% | 20% | 30% Girls/women, 70% Karimojongs | Number, % increase | Enrolement data | Annually | Start: End 30% 1000 trainees | VTI, Field team | M&E